Strategic Plan Addendum

August 2023

OKASLA Chapter Leadership Position and Committee Tactic Assignments

2023-2030 OKASLA Strategic Plan

- President	(P)	Pg. 2

  - Audit Committee	(AUD)

  - Operations Committee	(OPCom)

- President-Elect / Conference Planning Chair	(PE) / (CPC)	Pg. 3

  - Awards Committee	(AWD)

  - Central States Committee	(CSC)

- Immediate Past President	(IPP)

  - Tellers Committee	(TEL)

- Trustee	(TRUST)	Pg. 4

  - FASLA Chair	(FELLOW)

- Secretary	(SEC)

  - Nominations	(NOM)

  - Bylaws Committee	(BLC)

- Treasurer	(TRS)	Pg. 5

  - Scholarship Chair	(SCH)

  - Sponsorship Chair	(SPON)

- Advocacy Chair	(ADV)

- Associate-At-Large	(AAL)	Pg. 6

  - OSU & OU Student Representatives	(STUR)

- Member-At-Large	(MAL)	Pg. 7

  - OSU & OU Faculty Representatives	(FACR)

- Career Discovery Chair	(CD)	Pg. 8

- Communications Chair	(COM)	Pg. 9

  - Public Relations	(PR)

  - Social Media	(SM)

  - Website	(WEB)

- Events Chair	(EVTC)	Pg. 10

  - Oklahoma City Social Chair	(OKCS)

  - Tulsa Social Chair	(TSC)

  - Webinar Chair	(WBC)

- President (P)

- Investigate the feasibility, by March 2025, and establish a liaison/membership exchange with the following state allied organizations: ASCE (American Society of Civil Engineers), AIA (American Institute of Architects), APA (American Planning Association), ULI (Urban Land Institute), NAHB (National Association of Home Builders), ORPS (Oklahoma Recreation and Parks Society), NAWIC (National Association of Women in Construction), Sierra Club, ONLA (Oklahoma Nursery and Landscape Association), Urban and Community Forestry (Oklahoma Department of Agriculture) [with Trust, EVTC] [Connection.G1]

- Collaborate to provide an allied leader panel education session for the 2025 OKASLA state conference and as an annual stand-alone, joint CEU event [with Trust,  EVTC] [Connection.G1]

- Organize an annual allied leader panel education session at an allied organization event [with Trust,  EVTC] [Connection.G1]

- Identify and create a contact list of organizations that work with underrepresented/underserved communities [with Trust] [Connection.G1]

- Define and convey clear volunteer roles, responsibilities/duties by December 2023 (position descriptions) [ExCom] [Operations.G1]

- Create an OK ASLA leadership organization chart and workflow diagram by December 2023 [Operations.G1]

- Host leadership transition meeting/workshop including review of strategic plan annually [with ExCom] [Operations.G1]

- Host a Chapter Strategic Planning Session in 2029 [with ExCom] [Operations.G1]

- Conduct an annual review of communication and management systems (StarChpater, etc.) [with ExCom] [Operations.G2]

- Respond and create action plans based on member feedback [Operations.G2]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Audit Committee (AUD)

- Conduct an annual financial audit [with ExCom] [Operations.G3]

- Conduct an annual audit to see what has been accomplished [with ExCom] [Operations. G1]

- Operations Committee (OPCom)

- Investigate staffing support models (event-planner, shared executive director, etc.) [Operations.G1]

- President-Elect (PE) / Conference Planning Chair (CPC)

- Coordinate with President and Executive Committee to accomplish goals set forth during the Strategic Planning Meeting [with P, ExCom] [Connection.G1]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Host OK State Conference and award program [with AWD] [Community.G1]

- Awards Committee (AWD)

- Host OK State Conference and award program [with CPC] [Community. G1]

- Award the ASLA Honor & Merit certificate at OSU and OU [with FACR] [Community.G3]

- Coordinates the review of Chapter Award Submittals for the Annual Meeting [with ExCom] [Community.G1]

- Central States Committee (CSC) – during years when the Central States Conference is held in Oklahoma

- Coordinate location for the Central States Conference in 2027 (need to confirm year) [EVTC, ExCom] [Connection.G3]

- Coordinate speakers for the Central States Conference in 2027 (need to confirm year) [EVTC, ExCom] [Connection.G3]

- Coordinate with different ASLA chapter to review and select winners for the state awards submittal [P, ExCom]

- Immediate Past President (IPP)

- Review past chapter records/files by December 2024 to identify relevant documents that need to be scanned and organized [with SEC] [Operations.G1]

- Submit annual report survey to national ASLA [Operations.G1]

- Write and distribute an annual program report and treasurer report to membership [with TRS] [Operations.G2]

- Organize a Past-President meeting every 6-years, corresponding to the dates when the Central States Conference is in Oklahoma, to review relevant decisions made by past Presidents. [Operations. G1]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Tellers (TEL)

- Conduct annual leadership elections [with SEC] [Operations.G1]

- Trustee (Trust)

- Investigate the feasibility, by March 2025, and establish a liaison/membership exchange with the following state allied organizations: ASCE (American Society of Civil Engineers, AIA (American Institute of Architects), APA (American Planning Association), ULI (Urban Land Institute), NAHB (National Association of Home Builders), ORPS (Oklahoma Recreation and Parks Society), NAWIC (National Association of Women in Construction, Sierra Club, ONLA (Oklahoma Nursery and Landscape Association), Urban and Community Forestry (Oklahoma Department of Agriculture) [with P, EVTC] [Connection.G1]

- Organize an allied leader panel education session for the 2025 OKASLA state conference and as an annual stand-alone, joint CEU event [with P,  EVTC] [Connection.G1]

- Organize an annual allied leader panel education session at an allied organization event [with P, EVTC] [Connection.G1]

- Identify and create a contact list of organizations that work with underrepresented/underserved communities [with P] [Connection.G1]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- FASLA Chair (Fellow)

- Engage the current OKASLA Fellows to create a “Fellows Community” [Community.G1]

- Fellows spotlight in newsletter or website [with COM] [Community.G1]

- Actively encourage and recruit eligible members to submit OKASLA Fellows application ,and support application process [Community.G1]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Secretary (SEC)

- Solicit member and sponsor feedback on event preferences and needs via annual satisfaction survey [with EVTC, MAL] [Community.G1]

- Review past chapter records/files, by December 2024, to identify relevant documents [with IPP] [Operations.G1]

- Outline and create an archiving system by January 2025 [Operations.G1]

- Scan, archive, and shred paper copies of past chapter ExCom correspondence [with IPP] [Operations. G1]

- Post ExCom meeting reports to website [with WEB] [Operations.G2]

- Maintain an up-to-date records and archive system [Operations. G2]

- Make an intentional, personalized effort in recruiting future leaders [Operations.G1]

- Nominations (NOM)

- Conduct annual leadership elections [with IPP] [Operations.G1]

- Bylaws Committee (BLC)

- Ensure the OKASLA bylaws, administration policies and reporting requirements are in compliance with ASLA national. [Bylaws] [Operations.G1]

- Treasurer (TRS)

- Write and coordinate with COMM to distribute an annual program report and treasurer report to membership [with IPP, COM] [Operations. G2]

- File state and Federal taxes [Operations.G3]

- Annual review of scholarship contribution (OKC Community Foundation) [with SCH] [Operations.G3]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Scholarship Chair (SCH)

- Continue the OK ASLA scholarship program utilizing the OKC Community Foundation [Community.G3]

- Annual review of scholarship contribution (OKC Community Foundation) [with TRS] [Operations.G3]

- Sponsorship Chair (SPON)

- Outline sponsorship package and release by end Q3 annually [with ExCom] [Operations.G3]

- Identify and solicit new sponsorship partner [Operations.G3]

- Welcome new sponsors in eNews [COM, EVTC] [Community. G2]

- Outline sponsorship package and release by end Q3 annually [with SPON] [Operations.G3]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Advocacy Chair (ADV)

- Invite allied organizations to participate in OK ASLA advocacy efforts [with P, IPP] [Connection. G1]

- Collaborate with the OK Board of Architects (OBA) on state legislative initiatives [Voice. G1]

- Host an annual state advocacy day and promote member and student participation [FACR, STUR] [Voice. G1]

- Coordinate with the OBA to submit stories to the OBA Newsletter[with COM] [Voice. G1]

- Submit OBA updates that impact membership to the OK ASLA eNews [with COM] [Voice. G1]

- Host local member discussions/workshops on municipal codes/regulations [with EVTC] [Voice. G1]

- Promote member iAdvocate sign-up and participation in ASLA advocacy alerts [with COM] [Voice. G1]

- Host site tours with members and state/city/municipal elected officials and policy makers [with EVTC] [Voice. G1]

- Monitor issues of interest to the profession to identify and distribute member Call To Actions [with COMM][Voice. G1]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Associate-at-Large (AAL)

- Welcome new members with a personalized message [with MAL] [Community. G2]

- Provide new Associate members with targeted member benefits (LARE resource materials, etc.) [Community. G2]

- Invite new members to events via personal calls [with MAL] [Community. G2]

- Create a membership recruitment and retention plan by December 31, 2025 [with MAL] [Community. G2]

- Invite Oklahoma university landscape architecture faculty and students to join ASLA [Community. G2]

- Promote ASLA membership to Oklahoma landscape architecture faculty and students [with FACR,  STUR] [Community.G3]

- Host one ExCom meeting at Oklahoma universities, with accredited landscape architecture departments, per calendar year [with ExCom, FACR, STUR] [Community.G3]

- Encourage and coordinate with students to participate in state advocacy day, WLAM, Park(ing) Day, conference volunteerism and other events as appropriate [with EVTC, FACR, STUR, COMM] [Community.G3]

- Coordinate a student led, student hosted, and student focused session at the 2027 conference [with CPC, FACR, STUR] [Connection.G3]

- Conduct a year-end member satisfaction survey and coordinate with COMM to share results with membership [with MAL, COMM] [Operations.G2]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- OSU & OU Student Representatives (STUR)

- Promote professional member participation in the mentor and portfolio reviews at OSU and OU [with FACR, MAL, AAL] [Community.G3]

- Promote ASLA membership to OU and OSU faculty and students [with FACR, AAL] [Community.G3]

- Encourage Oklahoma university faculty to promote ASLA membership with  their students [with FACR, AAL] [Community.G3]

- Host one ExCom meeting at Oklahoma universities, with accredited landscape architecture departments, per calendar year [with ExCom, FACR, AAL] [Community.G3]

- Organize a student led, student led, and student focused session at the 2027 conference [with FACR, CPC, AAL] [Connection.G3]

- Member-at-Large (MAL)

- Prepare exit survey to be distributed to lapsed members [Community. G2]

- Conduct exit survey with lapsed members [Community.G2]

- Welcome new members with a personalized message [with AAL] [Community.G2]

- Invite new members to events via personal calls [with AAL, EVTC] [Community.G2]

- Create a membership recruitment and retention plan by December 31, 2025 [with AAL] [Community.G2]

- Invite non-member, state licensed landscape architects to join OK ASLA [Community.G2]

- Conduct an annual year-end member satisfaction survey and share results with membership [with AAL] [Operations.G2]

- Encourage Oklahoma university faculty to promote ASLA membership with their students [with FACR,  STUR] [Community.G3]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- OSU & OU Faculty Representatives (FACR)

- Promote professional member participation in the mentor and portfolio reviews at OSU and OU [with STUR] [Community.G3]

- Award the ASLA Honor & Merit certificate at OSU and OU [with AWD] [Community.G3]

- Promote ASLA membership to university, with an accredited landscape architecture department, faculty and students [with STUR, AAL] [Community.G3]

- Encourage faculty to promote ASLA membership to their students [with STUR, AAL] [Community.G3]

- Host one ExCom meeting at OU and OSU per calendar year [with ExCom & AAL & STUR] [Community.G3]

- Organize firm and site tours for OSU and OU students [Community.G3]

- Career Discovery Chair (CD)

- Host a statewide Minecraft event in 2025 and subsequently every three (3) years after that [Connection. G2]

- Spotlight member career discovery presentations and Scouts LA badge involvement [COM] [Connection. G2]

- Provide members with career discovery resources for their local community outreach posted to website [with COM] [Connection. G2]

- Support or sponsor existing STEM education programs that includes underserved/underrepresented communities (STEAM Engine, workshops, design camps, etc.) [P, TRUST] [Connection. G2]

- Connect with Discovery Lab Tulsa and OKC Science Museum to provide an informational / activity table during WLAM (World Landscape Architecture Month) [Connection. G2]

- Investigate the feasibility of a booth or education session at the Oklahoma School Counselor Association (OSCA) by March 2023 [Connection. G2]

- Expand engagement efforts to community and junior colleges, and environment design program students [Connection. G2]

- Utilize the Future Landscape Architects of America (FLAA) materials/resources for chapter and member career discovery outreach [Connection. G2]

- Coordinate participation in workshops or summer programs with affiliated professional organizations [Connection.G2]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Communications Chair (COM)

- Spotlight fellows in newsletter or website [with Fellow] [Community. G1]

- Spotlight members participating in the annual New Licensee Pinning Ceremony [Voice.G1]

- Spotlight university faculty and students who have been featured or spoke at conferences or awards ceremonies [Voice. G2]

- Spotlight members who have been featured in magazines or on other media [Voice.G2]

- Spotlight sponsors in eNews. [Voice.G2]

- Coordinate with the OBA to wubmit stories to the OBA Newsletter – ask Scott/Candace frequency & name [with ADV] [Voice. G1]

- Produce and distribute a monthly e-newsletter [ExCom] [Operations.G2]

- Create and distribute calendar invites to members for chapter events [ExCom]. [Operations.G2]

- Promote Central States Conference registration to OKASLA members, students, and allied organizations [COM] [Connection.G3]

- Promote events for allied professions that would affect members [Connection.G3]

- Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Public Relations (PR)

- Identify and elevate member pro-bono/grant-funded work, research and innovative projects for dissemination to local news outlets and social media platforms [with SM, WEB] [Voice.G2]

- Provide news releases and promote member award recipients to local media outlets [Voice. G2]

- Promote member and student member participation in WLAM and Park(ing) Day [with AAL] [Voice.G2]

- Request allied organization cross promotion for events [Connection. G1]

- Social Media (SM)

- Follow the Central States partner (Arkansas, St. Louis, Iowa, Prairie Gateway, and Nebraska/Dakotas) chapters social media accounts [Connection.G3]

- Follow state allied organizations social media accounts [Connection. G1]

- Link to OSU and OU socials media and subscribe to e-newsletters  [Voice. G2]

- Maintain a current and active social media presence [Voice. G2]

- Develop and implement, by March 31, 2025, a new outlet and social media strategy to maintain an active presence in the community and on the website and social media platforms including IG (Instagram), FB (Facebook), X, LI (LinkedIn)[Operations.G2]

- Website (WEB):

- Maintain an updated and current annual chapter event calendar on the website [with EVTC] [Community. G1]

- Provide members with career discovery resources for their own local community outreach (post to website) [with CD] [Connection.G2]

- Maintain an updated website [Operations.G2]

- Post the OK ASLA strategic plan to website [Operations. G2]

- Post ExCom meeting reports to website [with SEC] [Operations.G2]

- Events Chair (EVTC)

- Maintain updated annual chapter Events calendar by providing information to post on the website and in the eNews [with COM] [Community.G1]

- Organize a diversity of member events including family-friends and new professional options that occur at varied times and locations and have a variety of themes [with ExCom] [Community.G1]

- Organize an annual family-friendly chapter community service project [Community.G1]

- Host an annual member town hall in OKC and Tulsa [with ADV] [Community.G1]

- Invite students to participate in state advocacy day, WLAM, Park(ing) Day, conference volunteerism and other events as appropriate [with AAL] [Community.G3]

- Collaborate to provide an allied leader panel education session for the 2024 OKASLA state conference or as an annual stand-alone, joint CEU event [with P, Trust] [Connection.G1]

- Organize an annual allied leader panel education session at an allied organization event [with P, Trust] [Connection.G1]

- Organize a joint allied organization social/education event [Connection.G1]

- Form a planning committee in 2026 to host Central States in 2027 (need to confirm year) [Connection.G3]

- Host local member discussions/workshops on municipal codes/regulations [with ADV] [Voice. G1]

- Host site tours, one minimally per year, with members and state/city/municipal elected officials and policy makers [with ADV] [Voice. G1]Make an intentional, personalized effort in recruiting future leaders [with SEC] [Operations.G1]

- Oklahoma City Social Chair (OKCS)

- Coordinate minimally one local (1) social event per quarter [Community. G1]

- Tulsa Social Chair (TSC)

- Coordinate minimally one local (1) social event per quarter [Community. G1]

- Webinar Chair (WBC)

- Maintain updated webinar information provide to COMM for distribution to the membership including posting to chapter event calendar on the website and the eNews[Community.G1]

- Host monthly educational webinars [Community. G1]

- Explore recording webinars for posting on the website and quizzes, and report findings by March 31, 2025 [Community. G1]